## Sheet1
Sl No | Module | Task Name | Task Details | Start date | End Date
1 | Chapter with Home works | Create a new chapter and chapter contents to Subjects | Table Design for chapter Belongs to homework | 2022-10-20 | 2022-10-23
2 | Homework module | Create a new Homework for correspond chapter with subject | Table Design for homework ,CRUD Opeartion | 2022-10-25 | 2022-10-27
3 | Homework Notification | Notify to all students inside that class | Table Design,Notification details email,phonenumber | 2022-10-28 | 2022-10-29
4 | Homework Module | Students Submitted Homework and Verify Teacher ,Homework repots | Table Design,Students Submitted corresponding homeworks with add additional attachments,Teacher can verify homeworks | 2022-10-31 | 2022-11-02
5 | Timetable Module | Create a Time table for class | Table design,CRUD Operation,Period Creation,print Timetable | 2022-11-02 | 2022-11-07
6 | Homework Modulw | Homework Evaluation Teacjer | Table design,Evaluation Homeworks | 2022-11-07 | 2022-11-11
7 | teacher Daily reports | Teacher enter daily report to particular class ,its helpful for management | Table Design,Export repots with excel,pdf format | 2022-11-11 | 2022-11-13
8 | Alternative Teacher Assigen | If teacher leave that day alternative assigen another teacher | Table design,assigen new teacher particular period,and notify to teacher | 2022-11-14 | 2022-11-15
9 | Teacher Leave Module | Here techer can apply leave to managemnt,or head of school | Table design,Leave appy with reasons ,longs leaves enter from to dates | 2022-11-15 | 2022-11-17
10 | Teacher leave verification | Here management has verify application if approved leave application accepted or forward some other highr authority | Table design,CRUD Opeation | 2022-11-17 | 2022-11-19
11 | Student leave module | Students can apply for leave to class teacher | Table deisgn,Once student apply leave teacher can get notified,teacher forward to higher authority as well as parents,once verifid leave accepted | 2022-11-19 | 2022-11-22
12 | Transport Module | Students registration time ask Transport details | Table design,assigen transport to students | 2022-11-22 | 2022-11-24
13 | Transport Module | create drivers,assigen buses | Table design,create staff or drivers and assigen route to buses | 2022-11-24 | 2022-11-26
14 | Dormitary Module | Available rooms list,Add rooms | Table design,Add rooms,assigen students,Dormitory staff details | 2022-11-26 | 2022-11-30
15 | Inventory | Listout items,profit loss,Inventry management report, | Table design,Items adding ,CRUD Opeartion,Profit loss expense calculation | 2022-11-30 | 2022-12-03
16 | Inventory | Report management | Export report with details pdf excel | 2022-12-03 | 2022-12-06
17 | Library | Library management | Table design,CRUD Operation books,student return books information, | 2022-12-07 | 2022-12-11
18 | Examination | Exam management | Table design,add exams,exam types,subjects | 2022-12-12 | 2022-12-16
19 | Examination | Entry marks | Table design,mark entry with students | 2022-12-17 | 2022-12-20
20 | Examination | Publish result | Result with marks information | 2022-12-20 | 2022-12-23
21 | Exam attendance | Entry with students present exam | Table design ,Attendance entried | 2022-12-26 | 2022-12-29
22 | Fees | Fees module with information | Pay fees online,direct payment | 2022-12-29 | 2022-12-31
23 | Attendance students | Monthly,daily,subjectwise | Attendance for students ,table design | 2023-01-02 | 2023-01-07
24 | report management | Here get all reports ,like income expense,profit,students attendance, | Table design ,Report information | 2023-01-07 | 2023-01-09
25 | Document print module | get students,teachers ID CARD and students marksheet,scedules | Tbale design,Print documents information | 2023-01-09 | 2023-01-11
26 | online exam | Students can atten exam through online | Table design,Add exam with questions and answers,atudents atten exam and evaluating publish results | 2023-01-11 | 2023-01-20
27 | Wallet module | Parent can add student walltet amount | Table design,add wallet amount for students,also student pay amount from wallet | 2023-01-21 | 2023-01-23
28 | Shop | Create online shop in school | Table design,students buy products in shop and pay through wallet | 2023-01-23 | 2023-01-24
29 | Shop | Products,category,addtocart | Table design,CRUD Opeartion products,category information | 2023-01-24 | 2023-01-27
30 | Staff attendance | add staff attendance in highr authority | table design , add staff attendance | 2023-01-28 | 31-02-2023
31 | Staff payroll | Staff payroll information | table design,staff salery information ,payroll | 2023-02-01 | 2023-02-06
32 | Account information | Fund tranfer,Bank account information | Table design,Account information | 2023-02-06 | 2023-02-08
33 | Communication | Sms templates,email templates information | Create templates and edits | 2023-02-08 | 2023-02-10
34 | System setting information | Back end and front end settings |  | 2023-02-10 | 2023-02-12

## Sheet2
Notification Details Confirmation for Homwworks
a)email
b)Phone number (if phonenumber Buy a sms gateways)
Need to Explain Timtable structure
Need to Explain Homework Evaluation Process
Need to Explain Attendance Details
a) subjectwise attendance
b) daily attendance
c)monthly attendance
Need to Explain Invetory expense details
a) profit
a) profit
b)loss
c)income expense
d)vendor details
Need to Explain Fees structure details
Need to Explain Staff payroll